## Test for WorkPlanning Small
|  |  | Refinement | Refinement | VoC | VoC | Operations | Operations
Assignee | Plan | Hours | Eval Suite | Prompt Migrtion | Tyrell Corp | Buy N Large | Code Coverage >90% | Test Automation
Alex | 7/03 Plan - Actions |  | Resolve found bugs with eval suite |  |  |  | Write Unit tests to support Adoption for repo_a, repo_k and repo_y | Improve Regression Automation by creating Automated Tests for repo_a, repo_k
Alex | 7/03 Plan - Hours | 40 | 18 |  |  |  | 12 | 10
Alex | 7/03 Achieved - Actions |  | Enchanced Eval Suite capabilitiees based on report issues, still need to address the UI updates and retest |  |  |  | Completed, will go into this release | Wrote tests for repo_a and repo_k to be reviewed and approved by the SDET
Alex | 7/03 Achieved - Hours | 40 | 16 |  |  |  | 12 | 12
Alex | 7/10 Plan - Actions |  | Retest after UI updates and make changes as needed | Evaluate and Test required changes to support 3.3. to 4.o migration |  |  |  | Improve Regression Automation by creating additional Automated Tests for epo_y
Alex | 7/10 Plan - Hours | 40 | 10 | 24 |  |  |  | 6
Dan | 7/03 Plan - Actions |  |  |  | Fix erros on load of the UI screen |  | Write Unit tests to support Adoption for repo_d, repo_o and repo_u | Write Automation tests to support Adoption for repo_b, repo_m and repo_u
Dan | 7/03 Plan - Hours | 40 |  |  | 14 |  | 12 | 14
Dan | 7/03 Achieved - Actions |  |  |  | Adjusted layout to address bugs found |  | Completed, will go into this release | Tests create and reviwed by SDET.
Dan | 7/03 Achieved - Hours | 40 |  |  | 12 |  | 12 | 16
Dan | 7/10 Plan - Actions |  |  |  | Extend existing agent capabilities to support jpeg files: design, mocks, implementation
Dan | 7/10 Plan - Hours | 30 |  |  | 30
Ike | 7/03 Plan - Actions
Ike | 7/03 Plan - Hours | 0
Ike | 7/03 Achieved - Actions
Ike | 7/03 Achieved - Hours | 0
Ike | 7/10 Plan - Actions
Ike | 7/10 Plan - Hours | 0
Kyle | 7/03 Plan - Actions
Kyle | 7/03 Plan - Hours | 0
Kyle | 7/03 Achieved - Actions
Kyle | 7/03 Achieved - Hours | 0
Kyle | 7/10 Plan - Actions |  |  | Modify promps and test perfromance for migration to 4o |  |  | Write Unit tests to support Adoption for repo_i, repo_t
Kyle | 7/10 Plan - Hours | 40 |  | 32 |  |  | 8