## Test Template for Work Planning
|  |  | Refinement | Refinement | Refinement | Refinement | Refinement | VoC | VoC | VoC | Operations | Operations | Operations | Research
Assignee | Plan | Hours | Eval Suite | Prompt Migrtion | Outbound MCP | Learning Agent | Search | Tyrell Corp | Buy N Large | IniTech | Code Coverage >90% | Test Automation | Security / CVE | Research Projects
Alex | 7/03 Plan - Actions |  | Resolve found bugs with eval suite | [7 empty] | Write Unit tests to support Adoption for repo_a, repo_k and repo_y | Improve Regression Automation by creating Automated Tests for repo_a, repo_k | Provide Applicablity Analysis for 2 CVEs for repo_y
Alex | 7/03 Plan - Hours | 40 | 16 | [7 empty] | 12 | 10 | 2
Alex | 7/03 Achieved - Actions |  | Enchanced Eval Suite capabilitiees based on report issues, still need to address the UI updates and retest | [7 empty] | Completed, will go into this release | Wrote tests for repo_a and repo_k to be reviewed and approved by the SDET
Alex | 7/03 Achieved - Hours | 40 | 16 | [7 empty] | 12 | 12
Alex | 7/10 Plan - Actions |  | Retest after UI updates and make changes as needed | Evaluate and Test required changes to support 3.3. to 4.o migration | [7 empty] | Improve Regression Automation by creating additional Automated Tests for epo_y
Alex | 7/10 Plan - Hours | 40 | 10 | 24 | [7 empty] | 6
Bob | 7/03 Plan - Actions | [6 empty] | Design and Implement routing for Tyrell Corp |  |  | Document baseline code coverage for all repos on Confluence and Create corresponding Jira tickets for the entire group | Manage Automation Test Creation and Documentation.
Bob | 7/03 Plan - Hours | 40 | [5 empty] | 31 |  |  | 3 | 6
Bob | 7/03 Achieved - Actions | [6 empty] | Design Complete and passed Architecture Review. Development work began. Few Automated Tests created. Unable to complete further steps due to being blocked by the DevOps to enable MariaDB |  |  | Completed for majority of repos, 5 outstanding - following up on ownership | Ongoing coordination
Bob | 7/03 Achieved - Hours | 40 | [5 empty] | 27 |  |  | 3 | 10
Bob | 7/10 Plan - Actions | [6 empty] | Finalize changes and complete pre-Deployment end-to-end testing | Review Documentation, providet trade-offs for design and t-shirsizing |  | Complete baseline documentation and confluence updates for remaining repos | Manage AutoTest Creation and Documentation.
Bob | 7/10 Plan - Hours | 40 | [5 empty] | 22 | 10 |  | 2 | 6
Calvin | 7/03 Plan - Actions |  |  |  | Create UI mocks and implement related screens | [5 empty] | Write Unit tests to support Adoption for repo_c, and repo_n | Crate auto tests to add DEV Testing Regression. Make them automated for 2 repos
Calvin | 7/03 Plan - Hours | 40 |  |  | 20 | [5 empty] | 8 | 12
Calvin | 7/03 Achieved - Actions |  |  |  | Mocks reuquire refinement and board acceptance | [5 empty] | Completed, will go into this release | Created some automated unit tests, sill need more for both repos
Calvin | 7/03 Achieved - Hours | 40 |  |  | 20 | [5 empty] | 8 | 12
Calvin | 7/10 Plan - Actions |  |  |  | Mocks reuquire refinement and board acceptance. Followed by implementation. | [6 empty] | Create remaining automated unit tests to support DEV and Regression testing
Calvin | 7/10 Plan - Hours | 40 |  |  | 28 | [6 empty] | 12
Dan | 7/03 Plan - Actions |  |  |  |  | Deployment of Learning Agent. Demo and Confluence Documentation |  |  |  |  | Write Unit tests to support Adoption for repo_d, repo_o and repo_u | Write Automation tests to support Adoption for repo_b, repo_m and repo_u
Dan | 7/03 Plan - Hours | 40 |  |  |  | 14 |  |  |  |  | 12 | 14
Dan | 7/03 Achieved - Actions |  |  |  |  | Successful Deployement to DEV. |  |  |  |  | Completed, will go into this release | Tests create and reviwed by SDET.
Dan | 7/03 Achieved - Hours | 40 |  |  |  | 12 |  |  |  |  | 12 | 16
Dan | 7/10 Plan - Actions |  |  |  |  | Prepare Demo and Confluence Documentation |  | Extend existing agent capabilities to support jpeg files: design, mocks, implementation
Dan | 7/10 Plan - Hours | 40 |  |  |  | 10 |  | 30
Elli | 7/03 Plan - Actions |  |  |  | Resolve routing issues found in regression | [8 empty] | Run model performance analysis for new capabilities
Elli | 7/03 Plan - Hours | 40 |  |  | 26 | [8 empty] | 14
Elli | 7/03 Achieved - Actions |  |  |  | Completed, signed-off | [8 empty] | Documented outcomes and presented to the team
Elli | 7/03 Achieved - Hours | 40 |  |  | 28 | [8 empty] | 12
Elli | 7/10 Plan - Actions |  |  |  | End-to-end test upon UI comletion. Materials and Demo prep. | [8 empty] | Repeat analysis using suggestions provided
Elli | 7/10 Plan - Hours | 40 |  |  | 24 | [8 empty] | 16
Fatima | 7/03 Plan - Actions | [5 empty] | Improve latency for Core. Document by performing variety analysis. |  |  |  | Write Unit tests to support Adoption for repo_e
Fatima | 7/03 Plan - Hours | 40 |  |  |  |  | 36 |  |  |  | 4
Fatima | 7/03 Achieved - Actions | [5 empty] | Provided Analysis output |  |  |  | Delayed to next week
Fatima | 7/03 Achieved - Hours | 40 |  |  |  |  | 40 |  |  |  | 0
Fatima | 7/10 Plan - Actions | [5 empty] | Examine alternatives and impletement selected approach |  |  |  | Write Unit tests to support Adoption for repo_e
Fatima | 7/10 Plan - Hours | 40 |  |  |  |  | 36 |  |  |  | 4
Gina | 7/03 Plan - Actions | [8 empty] | Fix Parsing logic for processing non standarnd invoices | Write Unit tests to support Adoption for repo_f, repo_p and repo_x | Automation of test cases for three components across multile repos
Gina | 7/03 Plan - Hours | 40 | [7 empty] | 12 | 12 | 16
Gina | 7/03 Achieved - Actions | [8 empty] | Applied fix and deployed changes on dev for testing | Repo_f is non-production, no unit test requirements. Completed for repo_p. Repo_x will be delated into August relesae | Done
Gina | 7/03 Achieved - Hours | 40 | [7 empty] | 19 | 6 | 15
Gina | 7/10 Plan - Actions | [7 empty] | Routing capabilities changes | Validate applied changes. Fix multi-screen layout | Write Unit tests to support Adoption for repo_x
Gina | 7/10 Plan - Hours | 40 | [6 empty] | 10 | 24 | 6
Howard | 7/03 Plan - Actions | [7 empty] | Modify Routing capabilities | Fixed multi screen layout and participated in customer calls to highlight changes | Write Unit tests to support Adoption for repo_g, repo_r and repo_z
Howard | 7/03 Plan - Hours | 40 | [6 empty] | 20 | 8 | 12
Howard | 7/03 Achieved - Actions | [6 empty] | Triage P0 failure on the backend. Dependency on the other teams. | … |  | Completed for 2 repos. Repo_z will complete next week
Howard | 7/03 Achieved - Hours | 40 | [5 empty] | 32 |  |  | 8
Howard | 7/10 Plan - Actions | [7 empty] | Address re-opened similarity mechanism routing |  | Write Unit tests to support Adoption for repo_z | Support Regression and DEV testing by creating Automated Test cases. Have them reviewed and signed off by QA
Howard | 7/10 Plan - Hours | 40 | [6 empty] | 12 |  | 4 | 24
Ike | 7/03 Plan - Actions
Ike | 7/03 Plan - Hours | 0
Ike | 7/03 Achieved - Actions
Ike | 7/03 Achieved - Hours | 0
Ike | 7/10 Plan - Actions
Ike | 7/10 Plan - Hours | 0
Kyle | 7/03 Plan - Actions
Kyle | 7/03 Plan - Hours | 0
Kyle | 7/03 Achieved - Actions
Kyle | 7/03 Achieved - Hours | 0
Kyle | 7/10 Plan - Actions |  |  | Modify promps and test perfromance for migration to 4o | [6 empty] | Write Unit tests to support Adoption for repo_i, repo_t
Kyle | 7/10 Plan - Hours | 40 |  | 32 | [6 empty] | 8
Mark | 7/03 Plan - Actions |  |  |  |  | Demo to various teams. |  |  |  |  | Write Unit tests to support Adoption for repo_j, repo_w and repo_zz | Fix erros on Automated Tests for STED
Mark | 7/03 Plan - Hours | 40 |  |  |  | 10 |  |  |  |  | 12 | 18
Mark | 7/03 Achieved - Actions |  |  |  |  | Done |  |  |  |  | Completed, ready to merge when merge window is open | Completed
Mark | 7/03 Achieved - Hours | 40 |  |  |  | 8 |  |  |  |  | 12 | 20
Mark | 7/10 Plan - Actions
Mark | 7/10 Plan - Hours | 0
Lori | 7/03 Plan - Actions |  | Gather further requirments to support next set of changes. | [7 empty] | Write Unit tests to support Adoption for repo_i, repo_t |  |  | Research new Ontology capabilities
Lori | 7/03 Plan - Hours | 40 | 14 | [7 empty] | 8 |  |  | 18
Lori | 7/03 Achieved - Actions |  | Functional specs created. | Adjusted prompts due to migration efforts | [6 empty] | No time to help Kyle, will go back to him for next week |  |  | Provided highl level summary of research approaches
Lori | 7/03 Achieved - Hours | 40 | 12 | 10 | [6 empty] | 0 |  |  | 18
Lori | 7/10 Plan - Actions |  | pre-Architectual review and vetting with other teams | [7 empty] | Write Unit tests to support Adoption for repo_h, repo_s and repo_l |  |  | Generage comparison across various models and approaches for presentation review
Lori | 7/10 Plan - Hours | 40 | 8 | [7 empty] | 12 |  |  | 20